## Sheet1
|  |  |  | Sprint 1 | Sprint 1 | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5 | Sprint 6 | Sprint 6 | General Member Roles
0.0 NestWise- Agentic AI Reitrement Guide | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Member | Roles
[17 empty] | Ajinkya Naik | Team lead & co- Backend
1.0 Requirements Engineering | Week 1: Requirements Engineering | Anthony Jackson | co - backend & Langchain expert
1.1 Project sponsor specifies requirements | Week 1: Sponsor Requirements | Gareth Noble | Lead front-end & co-back-end
1.2 Submit project proposal (9/30/25) | Week 2: Project Proposal; Week 6: Submitted 9/30/25 | Gustavo | Co-front-end & prompt engineer
[17 empty] | Damilola Williams | lead-backend & RAG engineer
2.0 Design | Week 5: Elaboration
2.0 System Design | Week 5: System Design
2.0.1 Design Conceptual Target System | bar: Week 5 to Week 9
2.0.2 Gap Analysis | bar: Week 5 to Week 7
2.0.3 Working Demo for Midterm Presentation | bar: Week 7 to Week 9
2.1 Preliminary report | Week 7: Preliminary Report
2.1.1 Define scope with vision document | bar: Week 8 to Week 10
2.1.2 Identify project risks | bar: Week 8 to Week 10
2.1.3 Create project timeline | bar: Week 8 to Week 10
2.3 Midterm report (10/30/25) | Week 8: Midterm Report
3.0 Development | Week 8: Development | Member Roles for Each Sprint | Notes
3.1 Chatbot User Interface (UI) | Week 8: Chatbot User Interface (UI) | Ajinkya Naik will have team lead reposnsibilities.Anthony will serve as Project Manager. Gustavo will help the team to take notes on theTeam meetings and meetings with Dr.Kim. Gareth and Dami have no major responsibility as far as Sprints are concerned. | Team members will work on the same set of user stories during each sprint, but they will only work within their areas of expertise. In addition to that, some team members have additional responsibility (refer right)
3.1.1 Design and implement a basic front-end interface for the chatbot using modern web technologies. | bar: Week 8 to Week 10
3.1.2 Continuously enhance the UI based on backend requirements, user feedback, and functionality updates. | bar: Week 8 to Week 12
3.2 Workflow Pipeline Development | Week 8: Workflow Pipeline Development
3.2.1 Develop a python backend with llm | bar: Week 8 to Week 11
3.2.2 Use tools such as Langchain and Lang-graph to develop a basic workflow architechture | bar: Week 10 to Week 14
3.3 Retrieval-Augmented Generation (RAG) Integration | Week 10: Retrieval-Augmented Generation (RAG) Integration
3.3.1 Create a basic RAG tool | bar: Week 10 to Week 14
3.3.2 Faculty can set minimum requirements for their opportunities | bar: Week 10 to Week 14
3.4 A Chatbot Functionality and Optimization | Week 14: Chatbot Functionality and Optimization
3.4.1 Integrate the tools | bar: Week 14 to Week 16
3.4.2 Overcome the challenges | bar: Week 14 to Week 16
3.5 Final Report (12/12/25) | Week 15: Final Report
4.0 Testing | Week 14: Testing
4.1 Unit Testing | Week 14: Unit Testing
4.2 Integration Testing | bar: Week 14 to Week 16
4.3 System Testing | bar: Week 14 to Week 16
5.0 Deployment