## Sheet1
Note: We call each week a sprint internally. We grouped the first few stages into sprints later on. We have an extra week because we counted the pre-initiation week as part of the timeline.
2.0 Healthy Digital Habits | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
2.1 Pre-Initiation Stage | Week 1: Pre-Initiation Phase
Team formation | bar: Week 1
Sponsor introduction | bar: Week 1 to Week 2
Faculty advisor introduction | bar: Week 1 to Week 2
2.2 Inception | Week 3: Inception
V2 Environment startup | bar: Week 3 to Week 4
Environment standardization | bar: Week 3 to Week 4
Project documentation setup (OneDrive) | bar: Week 3
Week 4 sponsor update | bar: Week 3 to Week 4
Create git repo | bar: Week 3
Preliminary requirements documentation | bar: Week 4
2.3 Elaboration | Week 5: Elaboration
Week 5 sponsor update | bar: Week 5
Environment preparation | bar: Week 5 to Week 7
Week 7 presentation | bar: Week 7
Midterm deliverables | bar: Week 8 to Week 10
Prototyping | bar: Week 5 to Week 9
Prototyping Revisions | bar: Week 9 to Week 10
2.4 Development | Week 9: Development
2.41 Bug fixes | Week 9: Bug Fixes
Fixing Case Sensitive Username | bar: Week 9
Altering Cancel Button for Profile Page | bar: Week 10
Enter Key for Logging In | bar: Week 10
Fixing Active User Count | bar: Week 11 to Week 12
Add Loading Screen | bar: Week 15 to Week 16
Course creation runtime error | bar: Week 16 to Week 17
Module view runtime errors | bar: Week 16 to Week 17
2.42 Admin - course editor redesign | Week 9: Admin - Course editor redesign
Initial Admin Managment Landing Page changes
Course editor base-case | bar: Week 9 to Week 11
Course selection | bar: Week 9 to Week 11
Shfiting admin management content | bar: Week 9
Admin Managment Course Handling | bar: Week 9 to Week 10
Course creation modal | bar: Week 9 to Week 10
Course editor drag and drop side menu | bar: Week 9 to Week 13
Course Deletion Confirmation | bar: Week 12 to Week 13
Add Topic and Add Module Buttons | bar: Week 13 to Week 15
Expand the topic when a module is added (select it) | bar: Week 13 to Week 14
Garbage bin for modules | bar: Week 13 to Week 15
Question Modal for course editor | bar: Week 13 to Week 15
Grid System UI | bar: Week 14 to Week 15
Page Layout Persistence | bar: Week 15 to Week 16
Module Editor Pagination (w/o branching) | bar: Week 15 to Week 17
2.43 Parent Dashboard - Styling | Week 9: Parent Dashboard - Styling
Dashboard CSS Styling | bar: Week 9 to Week 10
Survey Screen Sliders | bar: Week 12 to Week 13
Survey Screen Updates | bar: Week 13 to Week 14
2.44 Site Wide | Week 9: Site Wide
Login screen beautification | bar: Week 10 to Week 11
Navbar Logo Functionality | bar: Week 12
Fixing navbar selection visuals | bar: Week 9
Replace HDH Logo | bar: Week 16
Card Height Fix | bar: Week 17
2.45 General Administration Tasks | Week 9: General Administration Tasks
Prettier and ESlint Integration | bar: Week 9 to Week 10
Fix Project Folder Hierarchy | bar: Week 10 to Week 11
2.5 Final Documentation | Week 14: Final Documentation
Final PPT | bar: Week 14 to Week 17
Final Software Architecture | bar: Week 15 to Week 16
Final Requirements Traceability Matrix | bar: Week 15 to Week 16
Final Project Plan | bar: Week 15 to Week 16
Final Product Backlog | bar: Week 15 to Week 16
Final Vision Document | bar: Week 15 to Week 16
Final Risk Assessment | bar: Week 15 to Week 16
Final Glossary | bar: Week 15 to Week 16
Final Requirements Model | bar: Week 16
Final Deliverables | bar: Week 16
Final Other Items | bar: Week 16
Final RTM | bar: Week 16 to Week 17
Final Demo | bar: Week 16 to Week 17