## Sheet1
|  |  |  | Sprint 1 | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4
0.0 Intelligent Plant Disease Identification System | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
1.0 Requirements Engineering | Week 1: Requirements Engineering
1.1 Meet with Dr Hajiarbabi | Week 1: Meet with Dr Hajiarbabi
1.2 Review Software Requirements | Week 1: Review Software Requirements
1.3 Determine Scheduling/Prototyping Software Systems | Week 1: Determine Scheduling/Prototyping Software Systems
1.4 Project Proposal Submission | Sprint 1 Week 4: Project Proposal Submission
2.0 Research | Week 1: Research
2.1 Study Materials from Faculty Advisor | Week 1: Study Materials from Faculty Advisor
2.2 Determing Plants/Symptoms/Diagnosis | Week 1: Determing Plants/Symptoms/Diagnosis
2.3 Find and Study External Resources/Materials | Week 1: Find and Study External Resources/Materials
2.4 Research Hosting Options | Week 2: Research Hosting Options
2.5 Test Server With Python Backend | Week 3: Test Server with Python Backend
3.0 Model Prototyping | Sprint 2 Week 5: Model Prototyping
3.1 Create High-Level UML | Sprint 2 Week 5: Create High Level UML
3.1 Create User Interface Sketches | Sprint 2 Week 5: Create UI Sketches
3.2 Determine Requirements for Inference Engine | Sprint 2 Week 6: Determine Requirements for Inference Engine
3.3 Determine Requirements for Knowledge Base | Sprint 2 Week 6: Determine Requirements for Knowledge Base
3.4 Determine Image Preprocessing Requirements | Sprint 2 Week 6: Determine Image Preprocessing Requirements
3.5 Draft CNN/RNN TensorFlow Models | Sprint 2 Week 7: Draft CNN/RNN TensorFlow Models
3.6 Preliminary Report (10/10/25) | Sprint 2 Week 7: Preliminary Report (10/10/25
4.0 Modeling | Sprint 3 Week 8: Modeling
4.1 Model CNN withTensorFlow/Python | Sprint 3 Week 8: Model CNN withTensorFlow/Python
4.2 Model RNN with TensorFlow/Python | Sprint 3 Week 8: Model RNN with TensorFlow/Python
4.3 Model Expert System with Experta/Python | Sprint 3 Week 8: Model Expert System with Experta/Python
4.4 Begin Testing Image Processing with ComputerVision (OpenCV) | Sprint 3 Week 10: Begin Testing Image Processing with ComputerVision (OpenCV)
4.5 Create Test Development Environment | Sprint 3 Week 10: Create Test Development Environment
4.6 Begin Developing UI | Sprint 3 Week 10: Begin Developing UI
4.7 Midterm Report (10/31/26) | Sprint 3 Week 10: Midterm Report
5.0 Developing/Testing/Integration | Sprint 4 Week 11: Developing
5.1 Use Hosting Platform | Sprint 4 Week 11: Use Hosting Platform
5.2 Develop RNN/CNN Architecture | Sprint 4 Week 11: Develop RNN/CNN Architecture
5.3 Develop A, B, C Plans for Hybrid System Design | Sprint 4 Week 12: Develop A, B, C Plans for Hybrid System Design
5.4 Develop OpenCV Architecture | Sprint 4 Week 12: Develop OpenCV Architecture
5.5 Create Information and Data Security Specifications | Sprint 4 Week 11: Create Information and Security Specifications
5.6 Integrate Machine Lerning Models with Image Processing | Sprint 4 Week 11: ntegrate Machine Lerning Models with Image Processing
5.7 Integrate Hybrid System and Machine Learning Models | Sprint 4 Week 11: Integrate Hybrid System with Machine Learning Models
5.8 Integrate UI Elements with Backend | Sprint 4 Week 11: Integrate UI Elements with Backend
5.9 Test Image Processing | Sprint 4 Week 11: Test Image Processing
5.10 Test Photo/Symptom Mapping | Sprint 4 Week 12: Test Photo/Symptom Mapping
5.11 Test Symptom/Disease Mapping | Sprint 4 Week 12: Test Symptom/Disease Mapping
5.12 Final Report | Sprint 4 Week 15: Final Report
Member Roles | bar: Week 1
Member | Week 1: Role
Josh Hanson | Week 1: Team Lead/ML
Eh Doh Kue Kyi | Week 1: Hybrid System/UI
Mason Lewis | Week 1: Hybrid System
David Markowski | Week 1: Hybrid System/UI
Matthew Murphy | bar: Week 1