## Sheet1
0.0 AI System for Classifying Skin Diseases from Images |  |  |  | Sprint 1 | Sprint 1 | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5 | Sprint 6 | Sprint 6 |  |  | 0.0 AI System for Classifying Skin Diseases from Images | Sprint 7 |  | Sprint 8 |  | Sprint 9 |  | Sprint 10 |  | Sprint 11 |  | Sprint 12 |  | Sprint 13 |  | Sprint 14
| Week 1 (08/25/2025) | Week 2 (09/01/2025) | Week 3 (09/08/2025) | Week 4 (09/15/2025) | Week 5 (09/22/2025) | Week 6 (09/29/2025) | Week 7 (10/06/2025) | Week 8 (10/13/2025) | Week 9 (10/20/2025) | Week 10 (10/27/2025) | Week 11 (11/03/2025) | Week 12 (11/10/2025) | Week 13 (11/17/2025) | Week 14 (11/24/2025) | Week 15 (12/1/2025) | Week 16 (12/08/2025) |  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
1.0 Inception | 1.0 Inception | [15 empty] | General Member Roles |  | 1.0 Inception
1.1 Project Team Formation | Team Formation | [15 empty] | Member | Roles | 1.1 Project Team Formation
1.2 Pick a Project from Sponsors | Pick Project | [15 empty] | Damian Williams | Team Lead, Back-end | 1.2 Pick a Project from Sponsors
1.3 Assign a Team Lead | Team Lead | [15 empty] | Maddie Sidwell | Full stack | 1.3 Assign a Team Lead
1.4 Submit Project Proposal (09/19/2025) |  | Project Proposal |  | (9/19/2025) | [12 empty] | Srinithi Yalamanchili | Front-end | 1.4 Submit Project Proposal (09/19/2025)
[17 empty] | Manuel Nieves Garcia | Front-end
2.0 Elaboration |  | 2.0 Elaboration | [14 empty] | Savannah Ostermeyer | Back-end | 2.0 Elaboration
2.1 System Design |  | 2.1 System Design | [16 empty] | 2.1 System Design
2.1.1 System Architecture Design |  | System Architecture Design | [16 empty] | 2.1.1 System Architecture Design
2.1.2 UI Design |  | UI Design | [16 empty] | 2.1.2 UI Design
2.1.3 Hardware and Software Design (Tech Stack) |  | Tech Stack | [16 empty] | 2.1.3 Hardware and Software Design (Tech Stack)
2.2 Preliminary Report (10/10/2025) |  |  |  |  | 2.2 Preliminary Report | [13 empty] | 2.2 Preliminary Report (10/10/2025)
2.2.1 Define Vision Document |  |  |  |  | Vision Document | [13 empty] | 2.2.1 Define Vision Document
2.2.2 Project Timeline |  |  |  |  | Timeline | [13 empty] | 2.2.2 Project Timeline
2.2.3 Access Technical Risks |  |  |  |  | Technical Risks | [13 empty] | 2.2.3 Access Technical Risks
2.2.4 Initial Requirements Model |  |  |  |  | Requirements Model | [13 empty] | 2.2.4 Initial Requirements Model
2.2.5 Bibliography |  |  |  |  | Bibliography | [13 empty] | 2.2.5 Bibliography
2.2.6 Midterm Report (10/31/2025) | [5 empty] | Midterm Report |  |  |  | (10/31/2025) | [8 empty] | 2.2.6 Midterm Report (10/31/2025)
3.0 Development | [5 empty] | 3.0 Development | [12 empty] | 3.0 Development
3.1 Frontend Web Application | [5 empty] | 3.1 Frontend Web App | [12 empty] | 3.1 Frontend Web Application
3.1.1 User Interface Design and Navigation | [5 empty] | UI Design / Nav | [12 empty] | 3.1.1 User Interface Design and Navigation
3.1.2 Frontend-Backend Communication | [9 empty] | Frontend / Backend Com | [8 empty] | 3.1.2 Frontend-Backend Communication
3.1.3 Chatbot Integration (Interaction with expert sytem model) | [18 empty] | 3.1.3 Chatbot Integration (Interaction with expert sytem model)
3.2 Convolutional Neural Network (CNN) | [5 empty] | 3.2 CNN | [12 empty] | 3.2 Convolutional Neural Network (CNN)
3.2.1 Dataset Preparation and Preprocessing | [5 empty] | Dataset Prep | [12 empty] | 3.2.1 Dataset Preparation and Preprocessing
3.2.2 Model Architecture and Training | [11 empty] | Model Training | [6 empty] | 3.2.2 Model Architecture and Training
3.2.3 Model Evaluation and Optimization | [18 empty] | 3.2.3 Model Evaluation and Optimization
3.2.4 Integration with Backend | [18 empty] | 3.2.4 Integration with Backend
3.3 Expert System | [5 empty] | 3.3 Expert System | [12 empty] | 3.3 Expert System
3.3.1 Knowledge Base Construction | [5 empty] | Base Construction | [12 empty] | 3.3.1 Knowledge Base Construction
3.3.2 Inference Engine Development | [12 empty] | Engine Development | [5 empty] | 3.3.2 Inference Engine Development
3.3.3 Explanation and Recommendation Module | [18 empty] | 3.3.3 Explanation and Recommendation Module
3.3.4 Chatbot Communication Layer | [18 empty] | 3.3.4 Chatbot Communication Layer
3.3.5 Final Report (12/12/2025) | [14 empty] | Final Report | (12/12/2025) |  |  | 3.3.5 Final Report (12/12/2025)
3.4 System Integration | [18 empty] | 3.4 System Integration | Week 1: 3.4 System Integration
3.4.1 Module Integration | [18 empty] | 3.4.1 Module Integration | Week 1: Module Integration
3.4.2 Integration Debugging | [18 empty] | 3.4.2 Integration Debugging | Week 4: Integration Debugging
3.4.3 MongoDB Database Integration | [18 empty] | 3.4.3 MongoDB Database Integration | Week 4: MongoDB Database Integration
4.0 Testing and Validation | [18 empty] | 4.0 Testing and Validation | Week 1: 4.0 Testing and Validation
4.1 Unit Testing | [18 empty] | 4.1 Unit Testing | Week 1: Unit Testing
4.2 Integration Testing | [18 empty] | 4.2 Integration Testing | Week 1: Integration Testing
4.3 System Testing | [18 empty] | 4.3 System Testing | Week 1: System Testing
4.4 Performance Evaluation | [18 empty] | 4.4 Performance Evaluation | Week 1: Performance Evaluation
4.5 User Testing | [18 empty] | 4.5 User Testing | Week 7: User Testing
5.0 Deployment | [18 empty] | 5.0 Deployment | Week 11: 5.0 Deployment
5.1 System Setup and Hosting | [18 empty] | 5.1 System Setup and Hosting | Week 11: System Setup and hosting
5.2 Model Integration | [18 empty] | 5.2 Model Integration | Week 11: Model Integration
5.3 Frontend Deployment | [18 empty] | 5.3 Frontend Deployment | Week 11: Frontend Deployment
5.4 Security and Data Protection | [18 empty] | 5.4 Security and Data Protection | Week 11: Security and Data Protection
5.5 System Demonstration and Documentation | [18 empty] | 5.5 System Demonstration and Documentation | Week 11: System Demonstration and Documentation
6.0 Final Final Report | [18 empty] | 6.0 Final Final Report | Week 11: 6.0 Final Final Report