## Product Backlog
Revision History
|  | Date | Version | Description | Name
|  | 2025-11-07 | 1 | Project Backlog | Shar Min
Backlog Items | Progress | 2025-12-07 | 2 | Prodect Backlog | Shar Min
1. Speech-to-Text Module
1.1 Audio upload into the system | DONE
1.3 Audio-to-text saved into a file | DONE
1.4 Add timestamps | DONE
1.5. Real-time transcript | DONE
2. Speaker Diarization Integration
2.1 Model setup and testing | DONE
2.2 Add speaker labels | DONE
2.3. Implement PII Redaction for transcript | DONE
3. OCR Integration
3.1 Upload scanned docs | DONE
3.2 Extract and store text | DONE
4. Dashboard
4.1 Clinical Dashboard | DONE
4.2 Tech Support Dashboard | DONE
4.3 Financial Dashboard | DONE
4.4 Login / Registeration | DONE
4.5 User authentication and access control | DONE
4.4 Dashboard with database & AI Server Link | DONE
5. Database Integration
5.1 Database Schema | DONE
5.2 Working database - MongoDB | DONE
5.3 Connect dashbord + AI Server to MongoDB | DONE
5.4 Set up SSH remote access | DONE
5.6 Database hosting (University or Home) - HOME | DONE
6. AI Server Integration
6.1 Add Whisper to AI Server | DONE
6.2 Add Speaker Diarization to AI Server | DONE
6.3 Add ORC to AI Server | DONE
6.4 Connect AI Server with Dashboard & Database | DONE
7. Data Analytic
7.1 Research EMR analytics and LLM use cases | DONE
7.2 Symptom word Extraction | DONE
7.3 Activity trend | DONE
7.4 Total time duration of all clients | DONE
7.5 Total words | DONE
8. Large Language Model
8.1 Implement Llama3 (Ollama) | DONE
8.2 PII Redaction (using Llama3) | DONE
8.3 SOAP Note / Summerizer (using Ollama) | DONE
9. Prototype Testing (Everything Together)
9.1 Whisper transcription accuracy test | DONE
9.2 Speech Diarization Test | DONE
9.3 OCR extraction test | DONE
9.4 Summerizer Test | DONE
10. Prototype Deploment
10.1 Prototype demo (with Dr Kim) | DONE