## Project Plan
Revision History
| Date | Version | Description | Name
| 2025-11-07 | 1 | Project Plan | Shar Min
| 2025-12-07 | 2 | Update Project Plan | Shar Min
Task ID | Task Name | Start Week | End Week |  | General Member Roles
1.0 | Define project idea and scope | 2 | 3 |  | Member | Roles
1.1 | Collect user and sponsor needs | 2 | 3 |  | Ahbisar Anand | Team Lead / AI
1.2 | Write and submit proposal | 2 | 3 |  | Shar Min | AI
1.3 | 1st Presentation - Project Proposal | 3 | 3 |  | Brayan Cana | AI
[5 empty] | Ali Mutlek | Dashboard / OCR
2.0 | System Design | 2 | 6 |  | Myles Edwards | Data Analyst
2.1 | Create architecture and use case diagrams | 2 | 6 |  | Dhyan Patel | Database
2.2 | 2nd Presentation - Midterm Presentation | 5 | 6
2.3 | Submit Preliminary Report | 5 | 6
3.0 | Development
3.1 | Dashboard | 4 | 10
3.2 | Implement Speech-to-Text (Whisper) | 5 | 10
3.3 | Add Speaker Diarization (Pyannote) | 5 | 13
3.4 | Add OCR and text extraction | 11 | 15
3.5 | Database Integrate (MongoDB) | 8 | 10
3.6 | AI Server | 14 | 14
3.7 | Midterm Report | 9 | 11
3.8 | Data Analysis | 11 | 15
3.9 | SOAP Note / Summerizer | 11 | 15
4 | Prototype & Testing
4.1 | Test the prototype (Eveerything Together) | 11 | 15
5 | Final
5.1 | Final Report | 15 | 16
5.2 | Final Presentation | 15 | 16