Project Title: Big League Barbers Web App

Version: 2.0

Document Type: Project Plan for Preliminary Report

Date: 10/09/2025

CS 46000-08

Project Plan

Team Members:

Prem Krishna Lavu

Connor Springer

Suli Alsallal

Myles Olagbegi

Grace Lueking

Project Overview

The Big League Barbers web application will be developed over an eight-week period following an Agile methodology. The goal is to create a functional, user-friendly appointment scheduling and rewards system accessible through web and mobile browsers. Each sprint will deliver incremental features that build toward a fully integrated and tested application.

3.2 Milestones and Deadlines

| Milestone | Description | Deliverables | Deadline |
| --- | --- | --- | --- |
| M1: Requirements Finalization | Finalize all project requirements and scope. | Vision document, glossary, requirements model, risk list | Oct 15, 2025 |
| M2: UI/UX Design | Develop low- and high-fidelity prototypes in Figma. | Design wireframes and user interface mockups | Oct 25, 2025 |
| M3: Backend Development | Set up Node.js server, database, and API endpoints. | Backend system and SQL Server database | Nov 5, 2025 |
| M4: Frontend Development | Implement frontend using React and connect to backend APIs. | Functional front-end components | Nov 15, 2025 |
| M5: Integration & Testing | Integrate all components and conduct full system testing. | Fully tested and integrated application | Nov 25, 2025 |
| M6: Final Review & Presentation | Finalize documentation and prepare project demo. | Final report and project presentation | Dec 10, 2025 |

3.3 Team Roles and Responsibilities

| Team Member | Role | Primary Responsibilities |
| --- | --- | --- |
| Prem Krishna Lavu | Front-End Developer / Project Planner | Develops the React-based UI, ensures responsiveness and accessibility, manages sprint timelines and milestone tracking. |
| Myles Olagbegi | Front-End Developer / UI Integration Lead | Implements React components, handles UX optimization, ensures communication between client-side and backend APIs. |
| Grace Lueking | Full Stack Developer / QA Coordinator | Manages integration between front-end and back-end, implements authentication and reward logic, leads QA and system testing. |
| Connor Springer | Back-End Developer / Database Architect | Designs and develops Node.js backend, manages SQL Server database, develops and tests RESTful APIs. |
| Suliman Alsallal | Back-End Developer / Database Integration Specialist | Manages database connectivity and queries, ensures data consistency, assists with GuestVision API integration. |

3.4 Sprint Structure and Goals

| Sprint | Duration | Focus Areas | Deliverables | Lead Roles |
| --- | --- | --- | --- | --- |
| Sprint 1 – Planning & Design | Weeks 1–2 | Finalize requirements, database schema, and low-fidelity design. | Vision document, glossary, database schema | Grace, Connor, Prem |
| Sprint 2 – Core Development | Weeks 3–4 | Build backend services for appointments, users, and authentication. | Backend API and database implementation | Connor, Suli |
| Sprint 3 – Front-End Integration | Weeks 5–6 | Develop and connect React frontend with backend APIs. | Functioning front-end with appointment booking and notifications | Prem, Myles |
| Sprint 4 – Testing & Finalization | Weeks 7–8 | Conduct system testing, bug fixes, and prepare for final demo. | Fully functional and tested system | Grace, Prem |

3.5 Development Responsibilities Overview

Front-End (Prem & Myles):

- Develop and test user-facing pages (login, dashboard, booking, rewards).

- Implement responsive UI using Tailwind CSS or Bootstrap.

- Manage API integration with React components.

Back-End (Connor & Suli):

- Develop Express.js routes for user authentication, booking, and rewards.

- Design and maintain SQL Server database schema.

- Integrate GuestVision API for real-time appointment data.

Full Stack (Grace):

- Oversee system integration between React and Node.js.

- Develop full-stack features like authentication, 7th Inning Stretch, and referral systems.

- Coordinate QA testing and manage bug reports.

3.6 Tools and Methodology

- Development Method: Agile (Scrum with 2-week sprints)

- Version Control: GitHub

- Design: Figma for UI/UX

- Backend: Node.js, Express.js

- Frontend: React

- Database: SQL Server (MSSQL)

- Testing Tools: Jest, Mocha, Supertest, Postman

- Collaboration: Discord for team communication

3.7 Feasibility and Resource Summary

Feasibility:
The project is feasible with the team's technical skills in React, Node.js, and SQL Server. The team has access to all necessary tools and software. The only dependency is API access to GuestVision, managed by Big League Barbers.

Resources:

- Hardware: Laptops/desktops for each developer.

- Software: Visual Studio Code, GitHub, SQL Server Management Studio, Figma.

- Communication: Discord, email, and weekly check-ins with the faculty advisor.

Estimated Effort:
Each team member will contribute approximately 35–45 hours, totaling around 180–200 hours for full project completion.