## Sheet1
Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Assigned To | Notes
1.0 Requirements & Planning | [9 empty] | Initial project setup | bar: Week 1
1.1 Define scope and requirements | [8 empty] | Prem, Connor | Gather requirements & define scope | bar: Week 1 to Week 2
1.2 Create glossary and risk list | [8 empty] | Myles, Grace | Glossary, risks, and constraints | bar: Week 1 to Week 2
1.3 Approve vision document | [8 empty] | All | Vision document finalized | bar: Week 2
2.0 Design | [9 empty] | UI/UX design and structure | bar: Week 2 to Week 3
2.1 Develop wireframes in Figma | [8 empty] | Prem, Myles | Low & high fidelity prototypes | bar: Week 3
2.2 Finalize database schema | [8 empty] | Connor, Suli | Database relationships and schema | bar: Week 3
3.0 Development | [9 empty] | Core development begins | bar: Week 4
3.1 Backend setup (Node.js, SQL Server) | [8 empty] | Connor, Suli | Backend configuration and APIs | bar: Week 4 to Week 5
3.2 Frontend setup (React) | [8 empty] | Prem, Myles | Frontend components and logic | bar: Week 4 to Week 6
3.3 Appointment system development | [8 empty] | Grace | Appointment management system | bar: Week 5 to Week 6
3.4 Notification and rewards integration | [8 empty] | Grace | Rewards and notifications | bar: Week 5 to Week 6
4.0 Testing | [9 empty] | Testing phase starts | bar: Week 6 to Week 7
4.1 Integration testing (API, DB, UI) | [8 empty] | Grace | Integration and debugging | bar: Week 7 to Week 8
4.2 System testing and bug fixes | [8 empty] | Prem | Final QA and fixes | bar: Week 8
5.0 Deployment & Review | [9 empty] | Deployment to test server | bar: Week 8
5.1 Deploy to test server | [8 empty] | Grace, Prem | Final review | bar: Week 8
5.2 Final presentation and demo | [8 empty] | All | Team presentation and report submission | bar: Week 8