## Sheet1
Clustergit |  |  | Sprint 1 | Sprint 1 | Sprint 2 | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5 | Sprint 6 | General Member Roles
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
| 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | Member | Roles
[17 empty] | Lauren | Lead, Backend Dev, Orchestration expert
1.0 Requirements Engineering | 2025-08-21: Requirements Engineering | Sean | Backend Dev, A+ Computers troubleshooter
1.1 Project Sponsor specifies requirements | 2025-08-21: Sponsor Requirements | Sasha | Backend Dev, Linux pro
1.2 Project Proposal (Sept 19) | 2025-09-04: Project Proposal (due 9/19) | Brandon | Backend Dev, Cybersecurity expert
[17 empty] | Conner | Backend Dev, Database expert
2.0 Elaboration | 2025-09-04: Elaboration
2.1 Cluster Infastructure | 2025-09-04: Cluster Infastructure
2.1.1 Prepare Pi's with Ubuntu Server | bar: 2025-09-04
2.1.2 Install and Configure k3s, test workloads | bar: 2025-09-11
2.2 Project Preliminary Report (Oct 10) | 2025-09-25: Preliminary Report (due 10/10)
2.2.1 Deploy Longhorn for Replication Across Nodes | bar: 2025-10-02
2.2.2 Test persistence of multi-GB giles across nodes
3.0 Development | 2025-10-09: Development
3.1 Containerization and Storage | 2025-10-09: Git Workflow | Member Roles For Each Sprint (1)
3.1.1 Layer Git-annex on Git to handle large file storage. | [16 empty] | Lauren - Hardware, troubleshooting | bar: 2025-10-09
3.1.2 Enable encryption for secure submissions. | [16 empty] | Sasha - Frontend, troubleshooting | bar: 2025-10-09
3.1.3 Provide simple CLI commands | [16 empty] | Conner - Frontend, VMs | bar: 2025-10-16
3.2 Midterm Report (Oct 31) | 2025-10-16: Midterm Report (due 31) | Brandon - Frontend, Docker, research
Sean - hardware, troubleshooting
| 2025-11-09: Testing | Sean - hardware, troubleshooting
4.0 Testing and Validation | 2025-11-09: Testing
4.0.1 Simulate 4-8 Gb Upload | bar: 2025-11-09
4.0.2 Measure Storage and Performance Usage | bar: 2025-11-16
4.0.3 Verify containerization, orchestration, encryption, replication, and retrievability | bar: 2025-11-23
4.1 Final Report (Dec 12) | 2025-11-30: Final Report (due 12/12)
Completion: | bar: 2025-08-21 to 2025-10-02
|  |  | Sprint 1 Notes: | spent lots of time researching and had limited time at the start for actual hand-on work because we had to wait to get internet in the lab so that we could configure them properly,