## Sheet1
|  |  |  | Sprint 1 | Sprint 1 | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5 | Sprint 6 | Sprint 6
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Members
Chance Biddle
1.0 Requirements Engineering | Week 1: Requirements Engineering | Cayla Hale
1.1 Project sponsor specifies requirements | Week 1: Sponsor Requirements | Ibigoni Inye-Tam
1.2 Submit project proposal (9/19/25) | Week 2: Project Proposal; Week 6: Submitted 9/19/25 | Mary Johnson
2.0 Stint 1 Research | Week 6: Research Topic Distribution and Collaboration
2.0 Planning | [16 empty] | Stretch Goals
2.0.1 Missed vs. Taken Meds Planning | Week 9: Planning and Research | Requirements
2.0.2 Research Audit Trail Options
2.0.3 Upcoming Meds Planning
2.0.4 Multi Langauge Support Research
2.1 Preliminary report (10/10/25) | Week 7: Preliminary Report
2.1.1 Define scope with vision document
2.1.2 Identify project risks
2.1.3 Create project timeline
2.3 Midterm report (11/1/25) | Week 10: Midterm Report
3.0 Development
3.1 Initial Implementation
3.1.1 Missed vs. Taken Meds Implementation | Week 11: Stint 1 Implementation
3.1.2 Research Audit Trail Options
3.1.3 Upcoming Meds Implementation
3.1.4 Multi Language Support Integration
3.2 Second stint Research
3.2.1 Medications Per Recipient Research | Week 13: Stint 2 Planning
3.2.2 File Sharing Planning
3.2.3 Notifications Planning and Research
3.2.4 Pinned Messages and DM Sorting Planning
3.3 Second Stint Implementation | Week 15: Stint 2 Implementation
3.3.1 Medications Per Recipient Implementation
3.3.2 File Sharing Implementation
3.3.3 Notifications Implementation
3.3.4 Pinned Messages and DM Sorting Implementation
3.4 Final Report (12/13/25) | Week 13: Final Report
4.0 Testing
4.1 Function Testing | Week 13: Function Testing
4.2 Integration to Main Branch | Week 15: Test Integration to Main Branch
4.3 System Testing