## Sheet1
0.0 AI System for Classifying Skin Diseases from Images |  |  |  | Sprint 1 | Sprint 1 | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5 | Sprint 6 | Sprint 6 | [5 empty] | Sprint 1 | Sprint 1 | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5 | Sprint 6 | Sprint 6
| Week 1 (08/25/2025) | Week 2 (09/01/2025) | Week 3 (09/08/2025) | Week 4 (09/15/2025) | Week 5 (09/22/2025) | Week 6 (09/29/2025) | Week 7 (10/06/2025) | Week 8 (10/13/2025) | Week 9 (10/20/2025) | Week 10 (10/27/2025) | Week 11 (11/03/2025) | Week 12 (11/10/2025) | Week 13 (11/17/2025) | Week 14 (11/24/2025) | Week 15 (12/1/2025) | Week 16 (12/08/2025) |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
1.0 Inception | 1.0 Inception | [15 empty] | General Member Roles
1.1 Project Team Formation | Team Formation | [15 empty] | Member | Roles
1.2 Pick a Project from Sponsors | Pick Project | [15 empty] | Damian Williams | Team Lead, Back-end
1.3 Assign a Team Lead | Team Lead | [15 empty] | Maddie Sidwell | Full stack
1.4 Submit Project Proposal (09/19/2025) |  | Project Proposal |  | (9/19/2025) | [12 empty] | Srinithi Yalamanchili | Front-end
[17 empty] | Manuel Nieves Garcia | Front-end
2.0 Elaboration |  | 2.0 Elaboration | [14 empty] | Savannah Ostermeyer | Back-end
2.1 System Design |  | 2.1 System Design
2.1.1 System Architecture Design |  | System Architecture Design
2.1.2 UI Design |  | UI Design
2.1.3 Hardware and Software Design (Tech Stack) |  | Tech Stack
2.2 Preliminary Report (10/10/2025) |  |  |  |  | 2.2 Preliminary Report
2.2.1 Define Vision Document |  |  |  |  | Vision Document
2.2.2 Project Timeline |  |  |  |  | Timeline
2.2.3 Access Technical Risks |  |  |  |  | Technical Risks
2.2.4 Initial Requirements Model |  |  |  |  | Requirements Model
2.2.5 Bibliography |  |  |  |  | Bibliography
2.2.6 Midterm Report (10/31/2025) | [5 empty] | Midterm Report |  |  |  | (10/31/2025)
3.0 Development | [5 empty] | 3.0 Development
3.1 Frontend Web Application | [5 empty] | 3.1 Frontend Web App
3.1.1 User Interface Design and Navigation | [5 empty] | UI Design / Nav
3.1.2 Frontend-Backend Communication | [9 empty] | Frontend / Backend Com
3.1.3 Chatbot Integration (Interaction with expert sytem model)
3.2 Convolutional Neural Network (CNN) | [5 empty] | 3.2 CNN
3.2.1 Dataset Preparation and Preprocessing | [5 empty] | Dataset Prep
3.2.2 Model Architecture and Training | [11 empty] | Model Training
3.2.3 Model Evaluation and Optimization
3.2.4 Integration with Backend
3.3 Expert System | [5 empty] | 3.3 Expert System
3.3.1 Knowledge Base Construction | [5 empty] | Base Construction
3.3.2 Inference Engine Development | [12 empty] | Engine Development
3.3.3 Explanation and Recommendation Module
3.3.4 Chatbot Communication Layer
3.3.5 Final Report (12/12/2025) | [14 empty] | Final Report | (12/12/2025)
3.4 System Integration
3.4.1 Module Integration
3.4.2 Integration Debugging
3.4.3 MongoDB Database Integration
4.0 Testing and Validation
4.1 Unit Testing
4.2 Integration Testing
4.3 System Testing
4.4 Performance Evaluation
4.5 User Testing
5.0 Deployment
5.1 System Setup and Hosting
5.2 Model Integration
5.3 Frontend Deployment
5.4 Security and Data Protection
5.5 System Demonstration and Documentation
6.0 Final Final Report