## Project Plan
|  |  |  | Sprint 1 | Sprint 1 | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5 | Sprint 6 | Sprint 6 | General Member Roles
0.0 Traffic Sign Recognition | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Member | Roles
[17 empty] | Rishigesh Rajendrakumar | Oversee Project Manager, ML model training
1.0 Project Launch | Week 1: Project Launch | Hayden Jones | Testing, Implementation
1.1 Project sponsor specifies requirements | Week 1: Requirements | Shreya Komarabattini | UI + UX, Datasets, Validation
1.2 Submit project proposal (Sept 19) | Week 3: Project Proposal | Aidan Mao | ML Model Training, Backend Development
[17 empty] | Jacob Heffelmire | UI + UX, Testing
2.0 Design | Week 4: Design
2.0 System Design | Week 4: System Design
2.0.1 Analysis of existing TSD architecture | bar: Week 5
2.0.2 Design system architecture
2.1 Preliminary report | Week 6: Preliminary Report
2.1.1 Define scope with vision document | bar: Week 6 to Week 7
2.1.2 Identify project risks | bar: Week 6 to Week 7
2.1.3 Create project timeline | bar: Week 7
2.3 Midterm report (10/24/31) | Week 10: Midterm Report
3.0 Development | Week 8: Development
3.1 Camera & image input | Week 8: Camera & Image Input
3.1.1 Implement live camera feed | bar: Week 8 to Week 9
3.1.2 Implement image/video upload for testing | bar: Week 8 to Week 9
3.2 Preprocessing Module | Week 10: Preprocessing
3.2.1 Image resizing and normalization | bar: Week 10 to Week 11
3.2.2 Handle lighting, angle, and occlusion variations | bar: Week 10 to Week 11
3.3 Recognition Engine | Week 12: Model Recognition
3.3.1 Train CNN model on GTSRB dataset | bar: Week 12 to Week 13
3.3.2 Integrate model with mobile app | bar: Week 12 to Week 13
3.3.3 Detect multiple signs per frame | bar: Week 12 to Week 13
3.4 Output & Feedback | Week 14: Output & Feedback
3.4.1 Display recognized signs visually with bounding boxes | bar: Week 14 to Week 15
3.4.2 Implement text-to-speech alerts | bar: Week 14 to Week 15
3.4.3 Show confidence scores for detected signs | bar: Week 14 to Week 15
3.5 Settings & Region Selection | Week 15: Settings & Region Selection
3.5.1 Allow users to select regional sign datasets | bar: Week 15
3.5.2 Alert Customization | bar: Week 15
Final Report
4.0 Testing | Week 10: Testing
4.1 Unit Testing | bar: Week 10 to Week 16
4.2 Integration Testing | bar: Week 10 to Week 16
4.3 System Testing | bar: Week 10 to Week 16
5.0 Deployment