Big League Barber’s Web App

Project Plan Document

Team Members:

Prem Krishna Lavu

Connor Springer

Suli Alsallal

Myles Olagbegi

Grace Lueking

### 7.1 Revised Project Plan

The project plan has been updated to reflect progress made during the first eight weeks and outlines the remaining sprints for the semester. The team follows an Agile Scrum methodology, using two-week sprints with clearly defined objectives and deliverables.

| Sprint | Duration | Focus / Goal | Key Deliverables | Team Members |
| --- | --- | --- | --- | --- |
| Sprint 1 | 9/6 – 9/20 | Initial setup, requirements gathering, and project proposal preparation. | Project Proposal Presentation, Figma layout assignment. | All members |
| Sprint 2 | 9/21 – 10/11 | Develop low- and high-fidelity Figma prototypes, assign report roles, begin Preliminary Report. | Completed Figma prototype, Preliminary Report draft. | All members |
| Sprint 3 | 10/12 – 10/25 | Refine prototype, prepare and deliver Midterm Presentation, plan next sprint structure. | Midterm Presentation, assigned next sprint backlog. | All members |
| Sprint 4 | 10/26 – 11/9 | Begin front-end and back-end integration. Establish working prototype with login, scheduling, and account systems. | Working prototype integrating React frontend with Node.js backend and SQL database. | Prem, Myles, Grace, Connor, Suli |
| Sprint 5 | 11/10 – 11/24 | Expand system functionality — implement rewards, referral, and notification systems. | Extended prototype with loyalty and referral logic. | Connor, Grace, Prem |
| Sprint 6 | 11/25 – 12/10 | Testing, debugging, and deployment preparation. | Final integrated system, test documentation, and demo. | All members |

### 7.2 Sprint 4 Goal and Backlog (Next Sprint)

Sprint Duration: October 26 – November 9, 2025
Sprint Goal:
Develop a working prototype that integrates front-end React components with the Node.js/Express backend and SQL Server database. Implement user authentication, appointment scheduling, and account management features.

#### User Stories for Sprint 4

| ID | User Story | Effort (hrs) | Priority | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| US-01 | As a user, I want to create an account so I can manage my appointments. | 8 | High | Account creation form validates all fields and stores data securely in SQL database. |
| US-02 | As a user, I want to log in securely so my data and appointments are protected. | 6 | High | Login with bcrypt password hashing and authentication using Express middleware. |
| US-03 | As a client, I want to schedule or cancel appointments to fit my availability. | 10 | High | Booking and cancellation successfully update database and reflect on dashboard. |
| US-04 | As a staff member, I want appointment changes to reflect in real time. | 6 | Medium | Appointment updates propagate through backend and API in under 3 seconds. |
| US-05 | As a user, I want to view and edit my profile information. | 5 | Medium | Profile page loads user data and updates correctly in SQL database. |

#### Sprint 4 Backlog (Task Breakdown)

| Task | Assigned To | Estimated Effort (hrs) | Description |
| --- | --- | --- | --- |
| Create login and registration forms (React) | Prem | 5 | Develop UI components for user authentication. |
| Connect frontend to backend API (login & signup) | Myles | 4 | Implement Axios calls to Express.js endpoints. |
| Build appointment scheduling routes in Express | Connor | 6 | Create backend routes for adding, updating, and cancelling appointments. |
| Design SQL tables for users and appointments | Suli | 5 | Create database schema and ensure relationships between entities. |
| Integrate authentication logic using bcrypt | Grace | 5 | Implement secure login and session handling. |
| Test data flow between frontend and database | Grace, Connor | 4 | Verify CRUD operations and data validation. |
| Set up automated testing for core functions | Grace | 3 | Write test cases for backend endpoints. |

#### Sprint 4 Deliverables

- Functioning login and registration system

- Appointment scheduling with database integration

- Profile management functionality

- Updated API documentation and data flow verification

#### Sprint 4 Expected Outcome

By the end of Sprint 4, the team will have a fully functional prototype demonstrating key system components (authentication, appointment scheduling, and account management) integrated across the front-end, back-end, and database layers. This sprint will lay the foundation for adding rewards, notifications, and advanced features in Sprint 5.