# NestWise – Agentic AI Retirement Guide

Risk Assessment Document

Version: 1.2

Team Members:

Ajinkya Abhijit Naik

Gareth Noble

Anthony Jackson

Gustavo Pereira Corsi da Silva

Damilola Williams

# Document History

| Date | Version | Description | Name(s) |
| --- | --- | --- | --- |
| 10/09/25 | 1.0 | Initial Risk Assessment Document creation | Anthony Jackson |
| 10/09/25 | 1.1 | Reviewed Content | Ajinkya Naik |
| 10/31/25 | 1.2 | Added Volatile Technology Risk | Anthony Jackson |

## Risk Assessment Summary

| ID |  | Risk | Likelihood | Impact | Severity | Mitigation Priority |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Technical integration complexity | Medium | High | High | High |
| 2 |  | Data privacy or leakage | Low | Critical | High | High |
| 3 |  | LLM inaccuracies | High | Medium | High | High |
| 4 |  | Team skill limitations | High | Medium | High | High |
| 5 |  | Scope creep | Medium | High | High | Medium |
| 6 |  | Schedule slippage / absences | Medium | Medium | Medium | Medium |
| 7 |  | Volatile Technology | High | Medium | Medium | Medium |

## 1. Technical Integration Complexity

Description: The system relies on multiple advanced technologies — LangChain, LangGraph, RAG, and the OpenAI API. Inexperience with these can lead to integration challenges and delays.

Project Impact: If integration fails or is poorly configured, the core conversational flow may not work as intended, leading to a non-functional prototype or missed deadlines.

Mitigation Strategy: Begin with proof-of-concept prototypes for each major component early in the development cycle. Use clear module boundaries and documentation.

Contingency Plan: If integration issues persist, simplify architecture (e.g., remove RAG or LangGraph temporarily) to ensure minimal viable functionality is achieved.

## 2. Data Privacy or Leakage

Description: Although PII is redacted and replaced with placeholders, there remains a risk of accidental data exposure through poor implementation, prompt injection, or local storage errors.

Project Impact: Exposure of user data—even locally—would undermine user trust and may disqualify the project from further development or evaluation.

Mitigation Strategy: Strictly enforce PII censorship and never transmit identifiable data to APIs. Conduct prompt injection tests. Document data flow clearly.

Contingency Plan: If a privacy flaw is discovered, immediately disable data submission and rebuild the data-handling layer with verified anonymization.

## 3. LLM Inaccuracies / Hallucinations

Description: The model may generate misleading or false financial information due to inherent LLM limitations or poor prompt design.

Project Impact: Inaccurate retirement plans could mislead users, damage credibility, and raise ethical concerns.

Mitigation Strategy: Constrain outputs using template-based generation, RAG-verified context retrieval, and post-processing sanity checks. Include visible disclaimers.

Contingency Plan: If persistent inaccuracies are detected, the system will limit outputs to verified RAG-supported information and disable speculative advice. A validation layer will block or replace misleading responses with safe fallback messages. The team will re-enable full functionality only after accuracy improves through testing and prompt refinement.

## 4. Team Skill Limitations

Description: The team is new to LLM orchestration frameworks like LangGraph and RAG.

Project Impact: Development delays or incomplete integrations may occur.

Mitigation Strategy: Assign members to specific technologies for deeper learning. Use shared documentation and weekly syncs.

Contingency Plan: Simplify scope and focus on a robust conversational core if timelines slip.

## 5. Scope Creep

Description: Adding “nice-to-have” features could overextend the team.

Project Impact: Delays or incomplete core features may result.

Mitigation Strategy: All new feature requests will go through a brief change review to assess their impact on time and scope before approval. The team will maintain a prioritized backlog of stretch goals, adding them only after core features are stable and milestones are met. This ensures innovation is balanced with disciplined delivery and schedule integrity.

Contingency Plan: Cut unfinished optional features to ensure core deliverables meet evaluation criteria.

## 6. Schedule Slippage / Absences

Description: Team absences or scheduling conflicts can disrupt progress.

Project Impact: Missed milestones and last-minute integration crunches.

Mitigation Strategy: Maintain a shared task board, ensure redundancy, and communicate asynchronously.

Contingency Plan: Prioritize the functional prototype over optional enhancements and request flexibility if needed.

## 7. Volatile Technology

Description: The technologies are cutting-edge and are constantly being updated and changed.

Project Impact: The code must use the most recent versions of the technologies, such as LangGraph and RAG, to ensure continued functionality and compatibility.

Mitigation Strategy: Stay informed about the latest releases of LangGraph and LangChain, monitor their changelogs, and implement automated version checks in the codebase to detect breaking updates early.

Contingency Plan: If a new library update causes instability, the team will temporarily revert to the last stable version while investigating the issue. Development will pause for affected components until compatibility is verified in a controlled environment. If necessary, the unstable dependency will be isolated or replaced to preserve overall system functionality.

## Risk Monitoring and Review

Review Frequency: Weekly

Responsible Roles: Team Lead (coordination), Technical Lead (integration), QA Lead (testing & data handling)

Escalation Process: High-severity risks are discussed in the next group meeting and documented in a log.

## Residual Risk and Acceptance

Given the exploratory nature of this project, a moderate to high risk tolerance is accepted — particularly around LLM performance variability and integration errors. The team will focus on mitigation through careful scope control and transparent communication rather than exhaustive prevention.