## Sheet1
Clustergit |  |  | Sprint 1 | Sprint 1 | Sprint 1 | Sprint 2 | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5 | Sprint 6 | General Member Roles
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
| 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | Member | Roles
[17 empty] | Lauren | Lead, Hardware expert
1.0 Requirements Engineering | 2025-08-21: Requirements Engineering | Sean | Hardware expert, IT
1.1 Project Sponsor specifies requirements | 2025-08-21: Sponsor Requirements | Sasha | orchestration expert, linux
1.2 Project Proposal (Sept 19) | 2025-09-04: Project Proposal (due 9/19) | Brandon | Cybersecurity
[17 empty] | Conner | Database expert, authentication
2.0 Elaboration | 2025-09-04: Elaboration
2.1 Cluster Infastructure | 2025-09-04: Cluster Infastructure
2.1.1 Prepare Pi's with Ubuntu Server | bar: 2025-09-04
2.1.2 Install and Configure k3s, test workloads | bar: 2025-09-11
2.2 Project Preliminary Report (Oct 10) | 2025-09-25: Preliminary Report (due 10/10)
2.2.1 Deploy Longhorn for Replication Across Nodes | bar: 2025-10-09
2.2.2 Test persistence of multi-GB giles across nodes
2.2.3 Redeploy Longhorn
2.2.4 IO benchmark and health check script
2.2.5 Configure Postgres server and annex remote
2.2.6 CLI wrapper
3.0 Development | 2025-10-09: Development
3.1 Containerization and Storage | 2025-10-09: Git Workflow | Member Roles For Each Sprint (1) | Member Roles For Each Sprint (2)
3.1.1 Layer Git-annex and update on Git to handle large file storage. | [16 empty] | Lauren - Hardware, troubleshooting | Lauren - Hardware, troubleshooting | bar: 2025-10-09
3.1.2 Enable encryption for secure submissions. | [16 empty] | Sasha - Frontend, troubleshooting | Sasha - Orchestration, implementation | bar: 2025-10-09
3.2 Midterm Report (Oct 31) | 2025-10-16: Midterm Report (due 31) | Brandon - Frontend, Docker, research | Brandon - Docker, containerization
3.2.1 integrate supabase authentication | bar: 2025-10-16
3.2.2 Provide simple CLI commands | bar: 2025-10-23
[17 empty] | Sean - hardware, troubleshooting | Sean - hardware, troubleshooting, IT
| 2025-11-09: Testing | Sean - hardware, troubleshooting
4.0 Testing and Validation | 2025-11-09: Testing
4.0.1 Simulate 4-8 Gb Upload | bar: 2025-11-09
4.0.2 Finalize DB schema | bar: 2025-11-16 to 2025-11-30
4.0.3 Measure Storage and Performance Usage | bar: 2025-11-16
4.0.4 Verify containerization, orchestration, encryption, replication, and retrievability | bar: 2025-11-23
4.1 Final Report (Dec 12) | 2025-11-30: Final Report (due 12/12)
4.1.1 Gather dashboard metrics | bar: 2025-11-30
4.1.2 Perform final tests
4.1.3 Final bug fixes | bar: 2025-12-07
Completion: | bar: 2025-08-28 to 2025-11-02
|  |  | Sprint 1 Notes: | spent lots of time researching and had limited time at the start for actual hand-on work because we had to wait to get internet in the lab so that we could configure them properly, | Sprint 2 Notes: | we had lots of network and hardware issues for this sprint, first with IT issues not allowing the pi's to connect to any server, then the power supplies not supplying enough power to the pi's to perform simple operations and crashing oftern, this sprint was filled with trials and tribulations, and they lead into the next sprint, but we leanred alot and managed to figure out many hardware issues early | Sprint 3 Notes: | more problems with the cluster this sprint, we were using netdata (by Jay's suggestion), but it ended up being that the SDHC cards were the wrong type (A1), and we needed SDHX, whenever there was a SD handshake in the cluster, there was a voltage mismatch, and everything got fried. So we had to get all new SD cards, reinstall everything on the cluster, and use a new Web Interface to view the cluster health. Now, with everything reinstalled, we are in a great position to speedily layer the stuff and inplement the database