## Project Plan
Sprint | Week Range | Objectives | Tasks | Deliverables | Responsible Members
Sprint 1 | Weeks 4–8 | Set up foundational architecture and complete initial backend and frontend setup. | • Initialize GitHub repository • Configure FastAPI environment with PostgreSQL • Implement basic React frontend structure • Define database schema and relationships • Create and test user registration & authentication (JWT) | Working prototype of login/signup with connected backend and database | All members
Sprint 2 | Weeks 9–12 | Develop and integrate major features for Clients and Staff. | • Implement Client profile management • Implement Staff profile creation and editing • Enable Clients to post and manage shifts • Enable Staff to browse and apply for shifts • Test REST API endpoints with Postman | Functional demo of Client and Staff roles with shift management features | All members
Sprint 3 | Weeks 13–16 | Enhance usability, introduce Superuser functionality, and conduct testing. | • Implement Superuser admin controls • Conduct integration and system testing • Improve UI/UX with React components • Finalize security features (role-based access) • Prepare documentation and midterm demo | Stable prototype with documentation and presentation-ready demo | All members
Sprint 4 | Weeks 1–5 (Next Semester) | Refine, test, and expand functionality based on feedback. | • Implement shift confirmation and feedback system • Integrate notifications and scheduling improvements • Conduct usability testing sessions • Refine database queries for performance | Fully functional version with end-to-end shift management workflow | All members
Sprint 5 | Weeks 6–9 (Next Semester) | Enhance design and scalability, prepare for final deployment. | • Optimize backend and frontend integration • Add optional features (2FA, shift filters, ratings) • Begin deployment setup (Render/AWS) • Conduct peer testing and debugging | Deployment-ready build with advanced features implemented | All members
Sprint 6 | Weeks 10–16 (Next Semester) | Finalize testing, polish UI, and prepare final presentation. | • Conduct final integration testing • Address bug reports and feedback • Complete user manuals and installation guide • Finalize capstone presentation materials | Final version submitted with documentation, demo video, and report | All members