## Project Plan
|  |  |  | Sprint 1 | Sprint 1 | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5 | Sprint 6 | Sprint 6 | General Member Roles
0.0 Traffic Sign Recognition | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Member | Roles
[17 empty] | Rishigesh Rajendrakumar | Oversee Project Manager, ML model training
1.0 Project Launch | Week 1: Project Launch | Hayden Jones | Testing, Implementation
1.1 Project sponsor specifies requirements | Week 1: Requirements | Shreya Komarabattini | UI + UX, Datasets, Validation
1.2 Submit project proposal (Sept 19) | Week 3: Project Proposal | Aidan Mao | ML Model Training, Backend Development
[17 empty] | Jacob Heffelmire | UI + UX, Testing
2.0 Design | Week 4: Design
2.0 System Design | Week 4: System Design
2.0.1 Analysis of existing TSD architecture | bar: Week 5
2.0.2 Design system architecture
2.1 Preliminary report | Week 6: Preliminary Report
2.1.1 Define scope with vision document | bar: Week 6 to Week 7
2.1.2 Identify project risks | bar: Week 6 to Week 7
2.1.3 Create project timeline | bar: Week 7
2.3 Midterm report (10/24/31) | Week 10: Midterm Report
3.0 Development | Week 8: Development
1.0 Frontend Setup | Week 8: Frontend Setup
1.1 Front end design | bar: Week 8 to Week 9
1.2 Create front end UI | bar: Week 8 to Week 10
1.3 Integrate camera functionality | bar: Week 8 to Week 10
1.4 UI-Backend Data Handling | bar: Week 8 to Week 11
2.0 Backend Setup | Week 8: Backend Setup
2.1 CPU Tensor Operations | bar: Week 8 to Week 9
2.2 Logger Class | bar: Week 8 to Week 9
2.3 GPU Tensor operations | bar: Week 10 to Week 12
2.4 OpenCV preprocessing | bar: Week 10 to Week 12
3.0 Model Training | Week 8: Model Training
3.1 Dataset Preparation | bar: Week 8 to Week 9
3.2 Setup model layout | bar: Week 8 to Week 12
3.3 Loss function and gradients | bar: Week 9 to Week 12
3.4 Data loading | bar: Week 9 to Week 14
3.5 Training loop | bar: Week 9 to Week 14
3.6 Parameter Management | bar: Week 9 to Week 14
3.7 Model Export | Week 16: Final Report
3.8 Model Testing
4.0 Output & feedback | Week 13: Output & Feedback
4.1 JNI integration | bar: Week 13 to Week 15
4.2 Display Results | bar: Week 13 to Week 15
4.3 Text-To-Speech | bar: Week 15
5.0 Testing & Optimization | Week 10: Testing
5.1 Unit & integration testing | bar: Week 10 to Week 16
5.2 Performance tuning | bar: Week 10 to Week 16
5.3 Device Compatibility | bar: Week 10 to Week 16